## Timeline-2
Research Activity |  |  | PI | Year 1 | Year 2 | Year 3
Data Collection | T1.1 | Design, implement and deploy data collection infrastructure | JCH
| T1.2 | Crowd-source collection of additional flight data
| T1.3 | Collect flight data from series of controlled experiments
| T1.4 | Establish fidelity & constraints on use of simulated data
Fault Detection | T2.1 | Use time-series analysis to baseline normal (in-control) flight patterns | NC
| T2.2 | Use time-series analysis to detect (out-of-control) flight patterns
Feature Interaction Analysis | T3.1 | Myra's #1 task | MC
| T3.2 | Myra's #2 task
| T3.3 | Myra's #3 task
Safety Assurance & Mitigation | T4.1 | Leverage crowdsourcing & pattern analysis to diagnose patterns | JCH
| T4.2 | Experimentally investigate mitigations for recurring flight anomalies | NC, MC
| T4.3 | Model patterns in Fault Trees and construct Safety Assurance cases | JCH
Architecture & Deploy | T5.1 | Design and develop onboard Dronolytics infrastructure | All
| T5.2 | Deploy infrastructure to support onboard & offboard Dronolytics
| T5.3 | Develop & test Dronolytics APIs, Dashboards, & user documents | ALL
| T5.4 | Work with NASA for beta testing.
Reporting | T6.1 | Monthly and annual reports, Meetings with NASA sponsors
| T6.2 | Dissemination of results via white papers, conferences, and journals